## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Register | 1 | 6 | 1 | 4 | 100%
Login/logout | 1 | 6 | 1 | 4 | 100%
Account public/private setting on an options menu webpage | 6 | 4 | 6 | 4 | 100%
Chat rooms for class | 11 | 6 | 11 | 6 | 100%
Invite people to class/chat rooms | 11 | 6 | 11 | 4 | 100%
Creating classrooms | 6 | 6 | 6 | 6 | 100%
Delete Account (and change names of comments to deleted user) | 6 | 6 | 6 | 6 | 100%
searchable accounts based on public and private setting | 11 | 6 | 11 | 7 | 100%
notes | 17 | 6 | 17 | 6 | 100%
share notes (markdown) | 23 | 6 | 23 | 6 | 100%
pomodoro timer | 17 | 6 | 17 | 6 | 100%
class faq | 17 | 4 | 17 | 6 | 100%
classroom invite link | 11 | 4 | 11 | 4 | 50%